## Blog Project Requirements
ID | Requirement |  | Type | Category | Status | Sprint
1 | Project Lifecycle Management | Scrum | Domain | Mandatorty | Yes
2 | Development Environment | ASP.NET Core 5 MVC and Bootstrap 5 (4.6) | Domain | Mandatorty | Yes
3 | DevOps | Git/Azure DevOps | Domain | Mandatorty | No
4 | IAM | ASP Identity system | Domain | Mandatorty | Yes
5 | Use 3rd party logins | Facebook or Google | Domain | Optional | No
6 | Database Server | MS SQL Server | Domain | Mandatorty | Yes
7 | Tables | ApplicationDbUser, Blog, Post, Comment, PostTag | Domain | Mandatorty | No
A | Authentication and Authorization Pages |  | Functional | Mandatorty
A.1 | Register Page | A user shall be able to with First name, Last Name, Email, Comment | Functional | Mandatorty | No
A.2 | A Login Page | A user shall be able to login an email and password field using ASP Identity | Functional | Mandatorty | No
B | A Create blog Page |  | Functional | Mandatorty
B.1 | User | the user should be able to create a new blog, with at least a title field and a blog description field. | Functional | Mandatorty | No
B.2 | Database | The database should store information about the blog's title, description, date created and author. | Functional | Mandatorty | No
B.3 | URL | examplesite.com/Blog/Create | Functional | Mandatorty | No
B.4 | Accessible to | signed on users | Functional | Mandatorty | No
C | A Create post Page |  | Functional | Mandatorty
C.1 | User | The user should be able to: 1. Add a new blog post for a given blog. title, blog text and tags. | Functional | Mandatorty | No
C.2 | Database | The database should store information about the posts | Functional | Mandatorty | No
C.3 | Search | Tags shall be used for post search. | Functional | Mandatorty | No
C.4 | URL | examplesite.com/Post/Create/4 (the URL for creating a post | Functional | Mandatorty | No
C.5 | Accessible to | signed on and owner of blog. | Functional | Mandatorty | No
D | A Blog edit Page |  | Functional | Mandatorty
D.1 | User | The user should be able to edit the current title and description and then save the changes. | Functional | Mandatorty | No
D.2 | Database | The changes shall be saved to the database | Functional | Mandatorty | No
D.3 | Search | N/A |  |  | No
D.4 | URL | examplesite.com/Blog/Edit/4 (the URL for editing blog with id = 4) | Functional | Mandatorty | No
D.5 | Accessible to | signed in and owner of blog | Functional | Mandatorty | No
E | A Post edit Page
E.1 | User | Should allow the user to edit the fields for the blog post (title, blog text and tags). | Functional | Mandatorty | No
E.2 | Dtaabase | When saving the changes, the last edited date field should be updated. | Functional | Mandatorty | No
E.3 | Search | N/A | Functional | Mandatorty | No
E.4 | URL | examplesite.com/Post/Edit/4 (the URL for editing the post with id = 4) | Functional |  | No
E.5 | Accessible to | Signed in and owner of the blog that has the post | Functional | Mandatorty | No
F | A Browse blogs Page
F.1 | Create two tabs | The tabs should allow the user to switch between browsing by the number of views a blog has or to browse posts by the most popular tags. (Clicking on the tabs may invoke Javascript). | Functional | Mandatorty | No
F.2 | URL | examplesite.com/Browse/Index | Functional | Mandatorty | No
F.3 | Accessible to | everyone, including anonymous users | Functional | Mandatorty | No
G | A Posts By Tags Page
G.1 |  | When a user clicks a tag in the browse page, this page should display all posts with that given tag. | Functional | Mandatorty | No
G.2 | URL | examplesite.com/Browse/Tags/4 (Shows posts for tag with id = 4) | Functional | Mandatorty | No
G.3 | Accessible to | Everyone, including anonymous users | Functional | Mandatorty | No
H | A Search Page
H.1 | User | This page should allow the user to search for blogs or posts. |  |  | No
H.2 | Database | N/A |  |  | Yes
H.3 | Search | 1. Search function shall be available on all pages. 2.Free search text to find matching blogs titles, post titles and post tags. 3. Display one list of matching blogs, and one list of matching post title or tag. 4. Clicking on a post in the result, should redirect the user to the blog view page with the month set to the month of the post. If a user clicks on Post X which is created 2014-03-22 it should display the blog view page for march. Clicking on a blog in the result should take the user to the blog view page with the latest month set |  |  | No
H.4 | URL | examplesite.com/Blogs/View/4?year=2015&month=4 (Shows posts in April 2015 for blog with id = 4)
H.5 | Accessible to | Everyone, including anonymous users |  |  | No
I | A Blog view page
I.1 | Displays the selected blog | At the top right side, the blog title together with the description should be displayed. |  |  | No
I.2 | Overview display | Below the description, an overview should be displayed with the number of post of the months. When clicking on a month, the page should reload and display the post made in that month only. (Tip is to use Query-string parameters). If I click on January, all posts made in January should be displayed. |  |  | No
I.3 | chronological order | In the middle, a filtered set of posts should be displayed. They should be displayed in chronological order. |  |  | No
I.4 | Display Comment | Below each post, display all comments associated with the post and an empty text area + button to allow the user to make a comment. Above the comment input it should display how many characters the user have typed into the box. |  |  | No
I.5 | Counting views is a rather complex matter | For the scope of this application it’s enough to increase the view count each time a user visits the page. (Making a get request). This means, that each time you load one or more posts from the database to show for the user, increase the view count by 1 for each) |  |  | No
I.6 | URL Requirement | examplesite.com/Blogs/View/4?year=2015&month=4 (Shows posts in April 2015 for blog with id = 4) |  |  | No
I.7 | Accessible to | Everyone, including anonymous users (It’s up to you if you want to allow anonymous users to post comments but you should motivate your decision) |  |  | No

## Sheet2 (hidden)
Type
Domain | Category | Status | Sprint
Functional | Mandatorty | No | 1
Non-functional | Optional | Yes | 2
3
4
5
6
7
8